## Feature Catalog
ID | Name | Program | Surface | Pillar | Description | Value / Why | Tool / Route / Screen added | Primary modules | New module? | Skills | Deps | Wave | Critical? | Gate: Arch | Gate: Security | Gate: Live | Owner | Risk
F00 | App-connections hardening & merge | Program 1 | Server | Foundation | Land in-flight persistent-login feature through gates; retrofit ADR-02; fix engine↔app-connections erosion | Lands the in-flight persistent-login feature safely and clears the biggest index.ts contention before Wave 1. | MCP tools: connect_app / confirm_app_connection / list_app_connections | app-connections.ts, engine.ts, index.ts | No | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 0 | Yes | Yes | Yes | Yes | — | Medium
F01 | Schema contracts | Program 1 | Server | Reliability | Template declares output JSON Schema; validated each run | Templates without a declared shape are unverifiable; schema contracts make drift and self-healing possible. | outputSchema on ManifestEntry + validateOutput() | types/schema.ts, storage, engine, index | No | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 1 | Yes | Yes | No | Yes | — | Medium
F02 | Drift detection | Program 1 | Server | Reliability | Diff live shape vs contract → flag; expose reusable diff primitive | Sites change silently; drift detection is the reliability trigger every self-heal/monitor feature reuses. | reusable diff primitive + drift flag on run result | drift.ts (new), engine, metrics, dashboard | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | F01 | 2 | Yes | No | No | Yes | — | Medium
F03 | Nightly re-verification + badges | Program 1 | Server | Reliability | verify-registry.mjs + nightly workflow → shields.io status | Community trust needs proof templates still work; nightly badges make verification visible and continuous. | scripts/verify-registry.mjs + nightly workflow + shields.io badge | scripts/verify-registry.mjs (new), workflow (new), registry-client | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 1 | Yes | No | No | Yes | — | Low
F04 | Self-healing templates | Program 1 | Server | Reliability | On drift, hand forensic DOM+old script to the calling agent → fix → verify → registry PR (never auto-merge) | Self-healing is the moat vs. computer-use: fix once, stay fixed automatically instead of degrading silently. | self-heal.mjs forensic handoff + registry PR helper | self-heal.mjs (new), engine, registry PR helper | Yes | test-driven-development, spec-driven-development, code-review-and-quality, security-and-hardening, browser-testing-with-devtools | F02, F03, F05 | 3 | Yes | Yes | Yes | Yes | — | High
F05 | synthesize_schema (agent-native) | Program 1 | Server | Agent-native | renderPage() → agent writes script → dry-run via executeExtraction → register | Lets any calling agent author a new template without a human writing Playwright by hand. | MCP tool: synthesize_schema (renderPage) | engine (renderPage), index | No | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 1 | Yes | Yes | No | Yes | — | Medium
F06 | Computer-use crystallization | Program 1 | Server | Agent-native | Agent solves unmapped site via computer-use → record → crystallize → optional auto-PR | Extends authoring to sites with no existing template at all via computer-use, then crystallizes to deterministic. | computer-use crystallization flow (record→crystallize→PR) | engine, storage, registry-client | No | test-driven-development, spec-driven-development, code-review-and-quality, security-and-hardening, browser-testing-with-devtools | F05 | 3 | Yes | Yes | Yes | Yes | — | High
F07 | Template pipelines / DAG | Program 1 | Server | Fabric | Chain templates; pipeline def + runner | Real workflows chain multiple templates; a pipeline runner turns single calls into composable capability. | MCP tool: run_pipeline (DAG runner) | pipeline.ts (new), types, index | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 3 | No | Yes | No | Yes | — | Medium
F08 | CEL conditional branching | Program 1 | Server | Fabric | Port Kriya's CEL evaluator; action-sequence branches on live state | Live-state branching (found item / no results / captcha) is required for realistic multi-step flows. | CEL branching in action-sequence templates | cel-eval.ts (new), engine, types | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 3 | No | Yes | No | Yes | — | Medium
F09 | Bidirectional flows | Program 1 | Server | Fabric | Read A → transform → form-fill write into B | Read+write flows (copy data from A into B) unlock RPA-replacement use cases, not just read-only scraping. | bidirectional read→transform→write flow | engine, pipeline | No | test-driven-development, spec-driven-development, code-review-and-quality, security-and-hardening, browser-testing-with-devtools | F07, F10 | 4 | No | Yes | Yes | Yes | — | High
F10 | Transform / normalize layer | Program 1 | Server | Fabric | jq-like output mapping | Raw extracted shapes rarely match what a consumer wants; jq-like mapping normalizes output once, centrally. | TransformSpec + applyTransform() (jq-like mapping) | transform.ts (new), types, index | Yes | test-driven-development, spec-driven-development, code-review-and-quality | — | 2 | No | Yes | No | No | — | Low
F11 | Signed provenance receipts | Program 1 | Server | Compliance | content-hash + version + schema-valid, signed, exportable | Regulated/financial consumers need tamper-evident proof of what was fetched and when. | signed, exportable provenance receipt | provenance.ts (new), engine, types | Yes | test-driven-development, spec-driven-development, code-review-and-quality | F01 | 3 | No | Yes | Yes | No | — | Medium
F12 | Policy engine | Program 1 | Server | Compliance | robots.txt/ToS awareness + per-template rate limits | Respecting robots.txt/ToS and rate limits is the ethical/legal floor for a scraping-adjacent product. | policy engine (robots.txt/ToS + rate limits) | policy.ts (new), engine | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | — | 4 | No | No | Yes | Yes | — | Medium
F13 | Encrypted credential vault | Program 1 | Server | Compliance | Encrypted secrets injected at run; distinct from app-connections | Some templates need real secrets (API keys, form values) distinct from browser login state. | MCP tool: vault get/set (encrypted secrets) | vault.ts (new), cookie-store, engine | Yes | test-driven-development, spec-driven-development, code-review-and-quality, security-and-hardening | F00 | 4 | No | Yes | Yes | No | — | High
F14 | Metrics 2.0 (SLA) | Program 1 | Server | Dist+Perf | Aggregate success-rate + latency (durationMs already captured) | Success-rate + latency SLAs are what a paying/consumer audience actually judges reliability by. | metrics dashboard aggregation (SLA) | metrics, dashboard | No | test-driven-development, spec-driven-development, code-review-and-quality, observability-and-instrumentation | — | 1 | No | No | No | No | — | Low
F15 | static-http template kind | Program 1 | Server | Dist+Perf | cheerio fast-path (no browser) — 10–50x faster for no-JS pages | Most pages need no browser at all; a cheerio fast-path is 10-50x cheaper and enables cloud-tier free execution. | static-http template kind (cheerio fast-path) | types, storage, engine, index (+cheerio) | No | test-driven-development, spec-driven-development, code-review-and-quality, performance-optimization, browser-testing-with-devtools | — | 3 | No | Yes | No | Yes | — | Medium
F16 | Short-TTL result cache | Program 1 | Server | Dist+Perf | in-mem Map TTL; key=templateId+url+cookie-present+proxy | Repeated identical calls in a short window shouldn't re-run a full browser session. | in-mem TTL result cache | result-cache.ts (new), index | Yes | test-driven-development, spec-driven-development, code-review-and-quality, performance-optimization | F14 | 2 | No | No | Yes | No | — | Low
F17 | OpenTelemetry observability | Program 1 | Server | Dist+Perf | Export ADR-04 measures as OTel | Standard OTel export lets ops teams plug APImeMCP into their existing observability stack. | OTel exporter adapter | otel adapter (new), engine | Yes | test-driven-development, spec-driven-development, code-review-and-quality, observability-and-instrumentation, browser-testing-with-devtools | F14 | 4 | No | No | No | Yes | — | Medium
F18 | Ephemeral hosted endpoint | Program 1 | Server | Dist+Perf | read-registry + zero-state HTTP endpoint; the substrate X01/X02 productize | A zero-state hosted endpoint is the substrate the entire cloud/consumer platform (X01/X02) is built on. | ephemeral hosted HTTP endpoint | hosted entry (new) | Yes | test-driven-development, spec-driven-development, code-review-and-quality, security-and-hardening, browser-testing-with-devtools | F11 | 5 | Yes | No | Yes | Yes | — | High
F19 | Close items 4/5 gaps | Program 1 | Server | Dist+Perf | apimemcp add CLI + lint-in-CI + live network-behavior check in verify-registry | Closes known roadmap gaps (CLI ergonomics, CI lint, live network check) blocking a clean v1 release. | apimemcp add CLI + CI lint + live network check | index (argv), verify.yml, verify-registry | No | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | F03 | 1 | No | No | No | Yes | — | Low
F20 | Change-monitoring mesh | Program 1 | Server | Creative | Diff template results over time → events (reuses F02 diff) | Turns one-shot diffing into a standing mesh of watched templates — the basis of the mobile monitor feature. | change-monitoring mesh (scheduler+notifier) | scheduler, notifier, drift | No | test-driven-development, spec-driven-development, code-review-and-quality, observability-and-instrumentation, browser-testing-with-devtools | F02 | 4 | Yes | No | No | Yes | — | Medium
F21 | NL→template one-shot | Program 1 | Server | Creative | 'make me an API for X' wrapper (F05+F06) | Removes the last friction step: an agent just says what it wants and gets a working template. | MCP tool: NL→template one-shot wrapper | index wrapper | No | test-driven-development, spec-driven-development, code-review-and-quality | F05, F06 | 5 | Yes | Yes | No | No | — | Medium
F22 | Semantic template discovery | Program 1 | Server | Creative | Search 'what can APImeMCP do for domain X' (local+registry) | Discoverability turns the registry from a list into an answerable "what can this do for me" surface. | MCP tool: discover_templates (semantic search) | discovery (new), registry-client | Yes | test-driven-development, spec-driven-development, code-review-and-quality | — | 2 | No | No | No | No | — | Low
F23 | Golden-snapshot regression | Program 1 | Server | Creative | Record known-good output; regression-detect | Regression protection so a template fix or engine change can't silently break output shape again. | golden-snapshot regression harness | snapshot infra (new) | Yes | test-driven-development, spec-driven-development, code-review-and-quality, browser-testing-with-devtools | F01 | 2 | No | No | No | Yes | — | Low
F24 | Marketplace reputation + semver | Program 1 | Server | Creative | Contributor reputation + template versioning/changelog | Reputation + semver make the registry trustworthy at scale as more contributors show up. | registry reputation + semver tooling | registry tooling, registry-client | No | test-driven-development, spec-driven-development, code-review-and-quality | F03, F14 | 5 | No | No | Yes | No | — | Medium
F25 | OpenAPI + client export | Program 1 | Server | Creative | Generate OpenAPI + typed client from a bundle | Standard OpenAPI/client export lets any existing tool integrate with zero APImeMCP-specific glue. | OpenAPI spec + typed client exporter | exporter (new), usage pattern | Yes | test-driven-development, spec-driven-development, code-review-and-quality | F01, F07 | 5 | No | No | No | No | — | Medium
W01 | Platform monorepo scaffold | Program 2 | Web | Web | Turborepo (apps/web, apps/mobile, packages/shared) + Vercel project + CI/CD | One monorepo with shared types is what makes web+mobile+cloud a coherent platform instead of three silos. | Turborepo scaffold (apps/web, apps/mobile, packages/shared) | apps/web, apps/mobile, packages/shared, turbo.json, vercel project | Yes | next-forge, deployments-cicd | — | P0 | No | Yes | No | No | — | Low
W02 | Cross-surface design system | Program 2 | Web | Web | Shared tokens; phosphor/void identity elevated; web+mobile | A single design system keeps web and mobile visually and behaviorally one product. | shared design tokens (web + mobile) | packages/shared/tokens, tailwind theme, RN theme | No | frontend-design, ui-ux-pro-max:design-system, shadcn | W01 | P0 | No | Yes | No | No | — | Medium
W03 | Registry browser + search | Program 2 | Web | Web | Browse/filter templates + verification badges | The registry has to be browsable before anyone can discover or run a community template. | route: /registry (browse/search) | apps/web/app/registry, registry API client | No | vercel:nextjs, vercel:shadcn, ui-ux-pro-max | W01, W02, X07 | P1 | No | No | No | No | — | Low
W04 | Template detail + schema/docs | Program 2 | Web | Web | Rendered docs + F01 schema + Run entry | Consumers need to see the schema/verification/provenance for a template before trusting a Run. | route: /registry/[id] (template detail) | apps/web/app/registry/[id], schema renderer | No | vercel:nextjs, dataviz | W03, F01 | P1 | No | No | No | No | — | Low
W05 | Web run console | Program 2 | Web | Web | Call X01; live results (JSON/table/image) | The core consumer loop — run a community API and see results — happens here. | route: /run (live run console) | apps/web/app/run, X01 client, SSE client | No | vercel:nextjs, dataviz, ui-ux-pro-max:ui-styling | W04, X01, X04 | P2 | Yes | No | No | Yes | — | Medium
W06 | Contribute flow | Program 2 | Web | Web | PR onboarding + gate explainer | Lowers the bar for new contributors, growing registry coverage (the flywheel). | route: /contribute | apps/web/app/contribute | No | vercel:nextjs, documentation-and-adrs | W03 | P2 | No | No | No | No | — | Low
W07 | Auth + accounts + dashboard | Program 2 | Web | Web | Clerk auth; monitors/history/keys | Accounts are required before monitors/history/API keys can exist at all. | route: /account (auth + dashboard) | apps/web/app/account, Clerk auth, dashboard | No | vercel:auth, vercel:vercel-storage | W01 | P1 | No | No | Yes | No | — | Medium
W08 | Landing + interactive hero | Program 2 | Web | Web | Vision pages + live compile-and-run hero demo | First impression and conversion surface; the live hero demo proves the product in 10 seconds. | route: / (landing + live hero demo) | apps/web/app/(landing), hero demo component | No | frontend-design, ui-ux-pro-max:ui-ux-pro-max, ui-ux-pro-max:banner-design | W02, X01 | P2 | No | No | No | No | — | Medium
X01 | Execution API gateway | Program 2 | Cloud | Cloud | POST/GET run; auth + rate-limit | The single gateway every web/mobile run call goes through; auth + rate-limit live here once. | API: POST/GET /api/run | api/run route (gateway), auth middleware, rate-limiter | Yes | vercel:vercel-functions, vercel:vercel-firewall, vercel:routing-middleware, vercel:auth | F18 | P1 | Yes | No | Yes | Yes | — | High
X02 | Safe registry-only runtime | Program 2 | Cloud | Cloud | Sandbox/@sparticuz/chromium; feasibility spike | Phones/browsers can't run Playwright — this sandboxed runtime is the only way they run templates at all. | sandboxed registry-only execution runtime | sandbox runtime, @sparticuz/chromium fallback, allowlist | Yes | vercel:vercel-sandbox, vercel:vercel-functions, security-and-hardening | F18, F15 | P1 | Yes | No | Yes | Yes | — | High
X03 | Durable jobs + heavy fallback | Program 2 | Cloud | Cloud | Vercel Workflow; heavy→self-host message | Multi-step/monitor flows exceed a single request's time budget; durable orchestration is required. | durable workflow orchestration (Vercel Workflow) | workflow definitions, retry/pause-resume | Yes | vercel:workflow | X02 | P2 | Yes | No | Yes | Yes | — | Medium
X04 | Results delivery | Program 2 | Cloud | Cloud | SSE/websocket + Expo push; ephemeral no-persist | Results have to reach the user live (web) or later (mobile push) without the site staying open. | SSE/websocket + Expo push delivery | SSE/ws handler, expo-push adapter | Yes | vercel:vercel-functions, expo push | X01 | P2 | No | No | Yes | No | — | Medium
X05 | Monitors service | Program 2 | Cloud | Cloud | Cron + F02 diff + push-on-change | Push-on-change monitors are the single biggest mobile consumer hook (price drop / restock / new filing). | cron monitors service | cron jobs, F02 diff consumer, push notifier | Yes | vercel:workflow, vercel cron | X03, F02, F20 | P3 | Yes | No | Yes | Yes | — | Medium
X06 | Encrypted cookies + vault | Program 2 | Cloud | Cloud | Per-user encrypted transit + optional vault | User-supplied cookies are sensitive; encrypted transit + opt-in vault is the trust floor for auth templates. | encrypted cookie transit + optional vault | cookie encryption, per-user vault store | Yes | security-and-hardening, vercel:vercel-storage | F13 | P2 | No | No | Yes | No | — | High
X07 | Registry mirror/cache DB | Program 2 | Cloud | Cloud | Postgres mirror + sync for fast catalog | A fast Postgres mirror avoids hitting the git registry on every browse/search request. | Postgres registry mirror/cache | postgres schema, registry sync job | Yes | vercel:vercel-storage, vercel:runtime-cache | — | P1 | No | No | No | No | — | Low
M01 | Expo app scaffold | Program 2 | Mobile | Mobile | iOS+Android, Expo Router, EAS, Clerk auth | The native app shell every mobile screen and EAS build depends on. | Expo app scaffold (Router, EAS, Clerk) | apps/mobile scaffold, expo-router, EAS config, Clerk auth | Yes | expo-react-native-typescript, vercel:auth | W01, W02 | P1 | No | Yes | No | No | — | Medium
M02 | Mobile design system impl | Program 2 | Mobile | Mobile | Native-look themed components | A native-feeling (not webview) app is required for store approval and consumer trust. | native themed component system | apps/mobile/theme, native components | No | frontend-design, expo-react-native-typescript, ui-ux-pro-max | W02, M01 | P1 | No | Yes | No | No | — | Medium
M03 | Browse/registry screens | Program 2 | Mobile | Mobile | Search/filter/badges/trending | Mobile users need to find a template before they can run or monitor it. | screen: Browse (registry search) | apps/mobile/screens/browse | No | expo-react-native-typescript | M02, X07 | P2 | No | No | No | No | — | Low
M04 | Run screen + result views | Program 2 | Mobile | Mobile | Inputs/cookies; JSON/table/image/share | "Run a community API from your phone" is the platform's headline consumer capability. | screen: Run (inputs + result views) | apps/mobile/screens/run, result views | No | expo-react-native-typescript, dataviz | M03, X01, X04 | P2 | Yes | No | No | Yes | — | Medium
M05 | Monitors + push | Program 2 | Mobile | Mobile | Subscribe + Expo push + notification handling | Push-on-change monitors delivered to the phone — the consumer wedge described in the vision. | screen: Monitors (subscribe + push) | apps/mobile/screens/monitors, push handler | No | expo push, expo-react-native-typescript | M04, X05 | P3 | Yes | No | No | Yes | — | Medium
M06 | Run history + account + cookies | Program 2 | Mobile | Mobile | History; device-encrypted cookies | Users need history + a safe place for their own cookies/credentials on-device. | screen: History + Account | apps/mobile/screens/history, apps/mobile/screens/account, device cookie store | No | expo-react-native-typescript, security-and-hardening | M04, X06 | P3 | No | No | Yes | No | — | Medium
M07 | App-store prep | Program 2 | Mobile | Mobile | Icons/splash/EAS submit; listing (fees = owner step) | Required before either app store will accept a public listing. | app-store assets + EAS submit config | app icons/splash, eas submit config, store listing | No | expo-react-native-performance, ui-ux-pro-max:banner-design | M01, M02, M03, M04, M05, M06 | P4 | No | No | No | No | — | Low

## Progress
ID | Name | Program | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | % Complete | Current gate | Blocked by | Owner | Reviewer | Overall status | Last updated
F00 | App-connections hardening & merge | Program 1 | Done | Todo | Todo | Todo | Todo | Todo | Done | Todo | Todo | Done | Done | Done | 41.67% | G7 | — | f00-builder | local-g4-security | Done | 2026-07-17T07:56:12.726Z
F01 | Schema contracts | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G8 | — | f01-builder | — | Done | 2026-07-17T09:12:37.704Z
F02 | Drift detection | Program 1 | Done | Done | N/A | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | f02-builder | — | Done | 2026-07-17T10:24:43.808Z
F03 | Nightly re-verification + badges | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | f03-builder | — | Done | 2026-07-17T09:48:38.792Z
F04 | Self-healing templates | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F05 | synthesize_schema (agent-native) | Program 1 | Done | N/A | N/A | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | f05-builder | — | Done | 2026-07-17T09:48:38.865Z
F06 | Computer-use crystallization | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F07 | Template pipelines / DAG | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | — | codex-f07-gate-reviewer | Done | 2026-07-17T13:14:10.819Z
F08 | CEL conditional branching | Program 1 | Done | Done | N/A | Done | Done | N/A | Done | Done | Done | Done | Done | Done | 100% | G7 | — | — | Codex_F08_gate_reviewer | Done | 2026-07-17T12:52:18.246Z
F09 | Bidirectional flows | Program 1 | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F10 | Transform / normalize layer | Program 1 | Done | Done | N/A | Done | Done | Done | Done | N/A | Done | Done | N/A | Done | 100% | G7 | — | — | — | Done | 2026-07-17T10:31:26.160Z
F11 | Signed provenance receipts | Program 1 | Todo | Todo | Todo | Todo | Todo | N/A | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
F12 | Policy engine | Program 1 | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F13 | Encrypted credential vault | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
F14 | Metrics 2.0 (SLA) | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | N/A | Done | 100% | G8 | — | f14-builder | — | Done | 2026-07-17T09:22:44.597Z
F15 | static-http template kind | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F16 | Short-TTL result cache | Program 1 | Done | Done | Todo | Done | Done | Done | Done | Done | Done | Done | N/A | Done | 90% | G7 | — | feat/F16-result-cache | — | Done | 2026-07-17T11:03:33.628Z
F17 | OpenTelemetry observability | Program 1 | Todo | Todo | N/A | Todo | Todo | N/A | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F18 | Ephemeral hosted endpoint | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F19 | Close items 4/5 gaps | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | — | — | Done | 2026-07-17T09:48:38.943Z
F20 | Change-monitoring mesh | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
F21 | NL→template one-shot | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
F22 | Semantic template discovery | Program 1 | Done | Done | Done | Done | Done | Done | Done | N/A | Done | Done | N/A | Done | 100% | G7 | — | f22-builder | — | Done | 2026-07-17T11:22:39.595Z
F23 | Golden-snapshot regression | Program 1 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 100% | G7 | — | codex | — | Done | 2026-07-17T11:10:29.082Z
F24 | Marketplace reputation + semver | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
F25 | OpenAPI + client export | Program 1 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W01 | Platform monorepo scaffold | Program 2 | Todo | Todo | N/A | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W02 | Cross-surface design system | Program 2 | Todo | Todo | N/A | Todo | Todo | N/A | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W03 | Registry browser + search | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W04 | Template detail + schema/docs | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W05 | Web run console | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
W06 | Contribute flow | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W07 | Auth + accounts + dashboard | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
W08 | Landing + interactive hero | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
X01 | Execution API gateway | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
X02 | Safe registry-only runtime | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
X03 | Durable jobs + heavy fallback | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
X04 | Results delivery | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
X05 | Monitors service | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
X06 | Encrypted cookies + vault | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
X07 | Registry mirror/cache DB | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
M01 | Expo app scaffold | Program 2 | Todo | Todo | N/A | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
M02 | Mobile design system impl | Program 2 | Todo | Todo | N/A | Todo | Todo | N/A | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
M03 | Browse/registry screens | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
M04 | Run screen + result views | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
M05 | Monitors + push | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | Todo | 0% | — | — | — | — | Not-started | —
M06 | Run history + account + cookies | Program 2 | Todo | Todo | Todo | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —
M07 | App-store prep | Program 2 | Todo | Todo | N/A | Todo | Todo | Todo | Todo | N/A | Todo | Todo | N/A | Todo | 0% | — | — | — | — | Not-started | —

## Schedule-Deadlines
ID | Name | Program | Wave | Planned start | Spec-done | Build-complete | Review-passed | Live-verify | Merged | Promote | Duration est (days) | Status vs plan | Owner
F00 | App-connections hardening & merge | Program 1 | 0 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 5 | On-track | —
F01 | Schema contracts | Program 1 | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F02 | Drift detection | Program 1 | 2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F03 | Nightly re-verification + badges | Program 1 | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F04 | Self-healing templates | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F05 | synthesize_schema (agent-native) | Program 1 | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F06 | Computer-use crystallization | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F07 | Template pipelines / DAG | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F08 | CEL conditional branching | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F09 | Bidirectional flows | Program 1 | 4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F10 | Transform / normalize layer | Program 1 | 2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F11 | Signed provenance receipts | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F12 | Policy engine | Program 1 | 4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F13 | Encrypted credential vault | Program 1 | 4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F14 | Metrics 2.0 (SLA) | Program 1 | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F15 | static-http template kind | Program 1 | 3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
F16 | Short-TTL result cache | Program 1 | 2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F17 | OpenTelemetry observability | Program 1 | 4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F18 | Ephemeral hosted endpoint | Program 1 | 5 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
F19 | Close items 4/5 gaps | Program 1 | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F20 | Change-monitoring mesh | Program 1 | 4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F21 | NL→template one-shot | Program 1 | 5 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
F22 | Semantic template discovery | Program 1 | 2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F23 | Golden-snapshot regression | Program 1 | 2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8 | On-track | —
F24 | Marketplace reputation + semver | Program 1 | 5 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
F25 | OpenAPI + client export | Program 1 | 5 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
W01 | Platform monorepo scaffold | Program 2 | P0 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
W02 | Cross-surface design system | Program 2 | P0 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
W03 | Registry browser + search | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
W04 | Template detail + schema/docs | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
W05 | Web run console | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
W06 | Contribute flow | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
W07 | Auth + accounts + dashboard | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
W08 | Landing + interactive hero | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X01 | Execution API gateway | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X02 | Safe registry-only runtime | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X03 | Durable jobs + heavy fallback | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X04 | Results delivery | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X05 | Monitors service | Program 2 | P3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
X06 | Encrypted cookies + vault | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
X07 | Registry mirror/cache DB | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
M01 | Expo app scaffold | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
M02 | Mobile design system impl | Program 2 | P1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
M03 | Browse/registry screens | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
M04 | Run screen + result views | Program 2 | P2 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 10 | On-track | —
M05 | Monitors + push | Program 2 | P3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
M06 | Run history + account + cookies | Program 2 | P3 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 6 | On-track | —
M07 | App-store prep | Program 2 | P4 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 4 | On-track | —